## Sheet1
PROJECT BORA | [13 empty] | Interest frozen at 2029.06.30. |  | No interest freeze
Task/Permit | Expected start date | Expected end date | Expected payment date | Year | Days in 1st year | Connected payment | Amount of payment (net, HUF) | Amount of payment (net, EUR) | Interest | Category | Settlement | FEP principal (net, EUR) | Comment | Amount with interest (net, EUR) | Interest amount (EUR) | Amount with interest (net, EUR) | Interest amount (EUR)
Inputs
MEKH capacity tender | 2026-09-01 | 2026-10-30 | 2026-10-30 | 2026 | 63 | Application fee | 6000000 | 16216.2162 | 12% | Fee | Cash | 16216.2162 |  | 21998.4814 | 5782.2651 | 23254.4973 | 7038.281 | FY rate (HUF/EUR) | 370
| 2026-09-01 | 2026-10-30 | 2026-10-30 | 2026 | 63 | Application bond | 806000000 | 2178378.3784 | 6% | Bond | Bank guarantee | 2178378.3784 | W+BESS | 2546553.4071 | 368175.0287 | 2621352.4003 | 442974.022 | Wind capacity (MW) | 200
| 2026-12-15 | 2026-12-30 | 2026-12-30 | 2026 | 2 | Performance bond | 5239000000 | 14159459.4595 | 6% | Bond | Bank guarantee | 14159459.4595 | W+BESS; application bond deducted; incl. 50% extra | 16388318.9705 | 2228859.511 | 16869687.1433 | 2710227.6838 | BESS percentage | 50%
Capacity allocation process - Application | 2026-12-30 | 2026-12-30 | 2026-12-30 | 2026 | 2 | Application bond (TSO) | 900000000 | 2432432.4324 | 12% | Bond | Cash deposit | 2432432.4324 | Refunded if project fails; deducted from conn. fee | 3234938.8005 | 802506.368 | 3419639.485 | 987207.0526 | BESS connection capacity (MW) | 100
Supplementary grid bond - 2027 | 2027-04-23 | 2027-04-23 | 2027-04-23 | 2027 | 253 | Supplementary grid bond annual instalment for 2027 | 1624000000 | 4389189.1892 | 6% | Bond | Bank guarantee | 4389189.1892 | Double amount; refunded if project fails | 4990221.3847 | 601032.1955 | 5136797.3547 | 747608.1655 | BESS storage capacity (MWh) – 4h | 400
Supplementary grid bond - 2028 | 2028-04-23 | 2028-04-23 | 2028-04-23 | 2028 | 253 | Supplementary grid bond annual instalment for 2028 | 812000000 | 2194594.5946 | 6% | Bond | Bank guarantee | 2194594.5946 | Refunded if project fails | 2353878.0116 | 159283.4171 | 2423017.6201 | 228423.0255 | Benchmark CAPEX - wind (HUF/MW) | 406000000
Supplementary grid bond - refund | 2028-03-13 | 2028-03-13 | 2028-03-13 | 2028 | 294 | Supplementary grid bond refund after BP | -1218000000 | -3291891.8919 | 6% | Refund | Bank guarantee | -3291891.8919 | Refund after BP (with time buffer) | -3553663.5898 | -261771.6979 | -3658044.0666 | -366152.1748 | Benchmark CAPEX - BESS (HUF/MWh) | 200000000
Supplementary grid bond - 2029 | 2029-04-23 | 2029-04-23 | 2029-04-23 | 2029 | 253 | Supplementary grid bond annual instalment for 2029 | 406000000 | 1097297.2973 | 6% | Bond | Bank guarantee | 1097297.2973 | 50% after building permit; refunded if project fails | 1110319.8168 | 13022.5195 | 1142932.8397 | 45635.5424 | Tender application | 2
Supplementary grid bond - 2030 | 2030-04-23 | 2030-04-23 | 2030-04-23 | 2030 | 253 | Supplementary grid bond annual instalment for 2030 | 0 | 0 | 6% | Bond | Bank guarantee | 0 | Paid by new owner; refunded if project fails | 0 | 0 | 0 | 0 | No. of top. lots | 28
Capacity allocation process - Awarding | 2027-01-14 | 2027-02-13 | 2027-02-13 | 2027 | 322 | Land reservation fee | 20590500 | 55650 | 20% | Land | Cash | 55650 | Reimbursed by buyer at exit; may be increased | 111300 | 55650 | 111300 | 55650 | No. of WTGs | 28
| 2027-01-14 | 2027-02-13 | 2027-02-13 | 2027 | 322 | Land purchase price | 45600000 | 123243.2432 | 20% | Land | Cash | 123243.2432 | Reimbursed by buyer at exit | 246486.4865 | 123243.2432 | 246486.4865 | 123243.2432 | No. of small power plants | 4
Grid connection plan | 2027-02-13 | 2028-08-11 | 2028-08-11 | 2028 | 143 | Design fee | 59142857.1429 | 159845.5598 | 20% | Devex | Cash | 159845.5598 |  | 319691.1197 | 159845.5598 | 319691.1197 | 159845.5598 | No. of municipalities | 10
| 2028-08-11 | 2028-08-11 | 2028-08-11 | 2028 | 143 | Administrative fee | 750544 | 2028.4973 | 20% | Devex | Cash | 2028.4973 |  | 4056.9946 | 2028.4973 | 4056.9946 | 2028.4973 | Bank guarantee interest | 6%
Grid connection agreement | 2029-01-08 | 2029-01-08 | 2029-01-08 | 2029 | 358 | Connection fee - Indirect | 13714261200 | 37065570.8108 | 12% | Connection fee | Cash | 37065570.8108 | TSO application bond deducted | 39190531.8475 | 2124961.0367 | 41428137.7205 | 4362566.9097 | Interest - cash deposits, fees, connection fee | 12%
| 2029-01-08 | 2029-01-08 | 2029-01-08 | 2029 | 358 | Connection fee - Direct | 508345804 | 1373907.5784 | 12% | Connection fee | Cash | 1373907.5784 | Depending on the SPV's declaration and TSO's decision | 1452673.3982 | 78765.8198 | 1535614.6183 | 161707.0399 | Interest - devex and land | 20%
Land contracting (additional land) | 2026-08-01 | 2027-06-01 | 2026-10-01 | 2026 | 92 | Legal fee, agent fee | 65580000 | 177243.2432 | 20% | Devex | Cash | 177243.2432 | To be paid | 354486.4865 | 177243.2432 | 354486.4865 | 177243.2432 | Minimum MOIC on 20% items | 2
Wind measurement | 2027-03-01 | 2028-02-29 | 2027-03-01 | 2027 | 306 | Met Masts | 147260000 | 398000 | 20% | Devex | Cash | 398000 | For 2 MM | 796000 | 398000 | 796000 | 398000 | FEP split | 70%
| 2027-01-01 | 2027-04-01 | 2027-01-01 | 2027 | 365 | Design fee | 3600000 | 9729.7297 | 20% | Devex | Cash | 9729.7297 | For 2 MM | 19459.4595 | 9729.7297 | 19459.4595 | 9729.7297 | DSA / success fee (EUR/MW/yr) | 2500
| 2028-02-29 | 2028-06-28 | 2028-06-28 | 2028 | 187 | EYA | 1665000 | 4500 | 20% | Devex | Cash | 4500 |  | 9000 | 4500 | 9000 | 4500 | DSA accrual start (signing) | 2026-10-26
Land reclassification | 2027-06-28 | 2027-12-25 | 2027-12-25 | 2027 | 7 | Administrative fee | 960000 | 2594.5946 | 20% | Devex | Cash | 2594.5946 |  | 5189.1892 | 2594.5946 | 5189.1892 | 2594.5946 | Interest freeze date | 2029-06-30
| 2027-06-28 | 2027-12-25 | 2027-07-28 | 2027 | 157 | Report fee | 8000000 | 21621.6216 | 20% | Devex | Cash | 21621.6216 |  | 43243.2432 | 21621.6216 | 43243.2432 | 21621.6216 | Exit date | 2029-12-31
Zoning plan modification | 2027-12-25 | 2028-06-22 | 2028-02-23 | 2028 | 313 | Design fee | 50000000 | 135135.1351 | 20% | Devex | Cash | 135135.1351 |  | 270270.2703 | 135135.1351 | 270270.2703 | 135135.1351 | Purchase price (EUR/MW) | 150000
Municipality donation | 2027-12-25 | 2028-06-22 | 2028-02-23 | 2028 | 313 | Donation | 35000000 | 94594.5946 | 20% | Devex | Cash | 94594.5946 |  | 189189.1892 | 94594.5946 | 189189.1892 | 94594.5946 | Transaction costs (EUR) | 500000
Environmental assessment | 2026-12-30 | 2027-12-30 | 2027-12-30 | 2027 | 2 | Bird-bat monitoring | 14832000 | 40086.4865 | 20% | Devex | Cash | 40086.4865 | To be paid | 80172.973 | 40086.4865 | 80172.973 | 40086.4865
| 2027-12-30 | 2028-04-28 | 2028-04-28 | 2028 | 248 | Administrative fee | 40000 | 108.1081 | 20% | Devex | Cash | 108.1081 |  | 216.2162 | 108.1081 | 216.2162 | 108.1081
| 2027-12-30 | 2028-03-29 | 2028-03-29 | 2028 | 278 | Assessment fee | 32610000 | 88135.1351 | 20% | Devex | Cash | 88135.1351 |  | 176270.2703 | 88135.1351 | 176270.2703 | 88135.1351 | FEP proposal - Exit: 2029.12.31.
Other project development | 2026-12-30 | 2027-07-28 | 2027-07-28 | 2027 | 157 | Geotechnical assessment fee | 8000000 | 21621.6216 | 20% | Devex | Cash | 21621.6216 |  | 43243.2432 | 21621.6216 | 43243.2432 | 21621.6216 |  | Interest frozen at 2029.06.30. |  | No interest freeze
| 2026-12-30 | 2027-07-28 | 2027-06-28 | 2027 | 187 | Archaeological | 8000000 | 21621.6216 | 20% | Devex | Cash | 21621.6216 |  | 43243.2432 | 21621.6216 | 43243.2432 | 21621.6216 |  | EUR | EUR/MW | EUR | EUR/MW
| 2026-12-30 | 2027-07-28 | 2027-06-28 | 2027 | 187 | Topography | 8000000 | 21621.6216 | 20% | Devex | Cash | 21621.6216 |  | 43243.2432 | 21621.6216 | 43243.2432 | 21621.6216 | Buyer reimbursement (land, bonds, conn. fee) | 62024317.5784 | 310121.5879 | 62024317.5784 | 310121.5879
Building permit - Turbines | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2028 | 339 | Administrative fee | 4590000 | 12405.4054 | 20% | Devex | Cash | 12405.4054 |  | 24810.8108 | 12405.4054 | 24810.8108 | 12405.4054 | Exit premium | 30000000 | 150000 | 30000000 | 150000
| 2027-08-01 | 2028-01-28 | 2028-01-28 | 2028 | 339 | Design fee | 138000000 | 372972.973 | 20% | Devex | Cash | 372972.973 |  | 745945.9459 | 372972.973 | 745945.9459 | 372972.973 | Transaction costs | 500000 | 2500 | 500000 | 2500
Cable right | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2028 | 339 | Administrative fee | 45000000 | 121621.6216 | 20% | Devex | Cash | 121621.6216 |  | 243243.2432 | 121621.6216 | 243243.2432 | 121621.6216 | Total interest | 9312494.2254 | 46562.4711 | 12519113.3095 | 62595.5665
| 2027-08-01 | 2028-01-28 | 2028-01-28 | 2028 | 339 | Design fee | 74896683.6735 | 202423.4694 | 20% | Devex | Cash | 202423.4694 |  | 404846.9388 | 202423.4694 | 404846.9388 | 202423.4694 | DSA | 1590277.7778 | 7951.3889 | 1590277.7778 | 7951.3889
| 2027-08-01 | 2028-01-28 | 2027-11-29 | 2027 | 33 | Compensation | 15000000 | 40540.5405 | 20% | Devex | Cash | 40540.5405 |  | 81081.0811 | 40540.5405 | 81081.0811 | 40540.5405 | Distributable proceeds | 18597227.9968 | 92986.14 | 15390608.9128 | 76953.0446
Building permit - Substation, switching station | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2028 | 339 | Administrative fee | 6000000 | 16216.2162 | 20% | Devex | Cash | 16216.2162 |  | 32432.4324 | 16216.2162 | 32432.4324 | 16216.2162 | Devex (deducted from FEP) | 2782714.2483 | 13913.5712 | 2782714.2483 | 13913.5712
| 2027-08-01 | 2028-01-28 | 2028-01-28 | 2028 | 339 | Design fee | 45178571.4286 | 122104.2471 | 20% | Devex | Cash | 122104.2471 |  | 244208.4942 | 122104.2471 | 244208.4942 | 122104.2471
Building permit - BESS | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2028 | 339 | Administrative fee | 4590000 | 12405.4054 | 20% | Devex | Cash | 12405.4054 |  | 24810.8108 | 12405.4054 | 24810.8108 | 12405.4054 | Profit FGX | 13018059.5978 | 65090.298 | 10773426.2389 | 53867.1312
| 2027-08-01 | 2028-01-28 | 2028-01-28 | 2028 | 339 | Design fee | 70000000 | 189189.1892 | 20% | Devex | Cash | 189189.1892 |  | 378378.3784 | 189189.1892 | 378378.3784 | 189189.1892 | Profit FGX + interest - Devex | 19547839.5749 | 97739.1979 | 20509825.3001 | 102549.1265
HEPURA permit | 2029-01-08 | 2029-03-24 | 2029-01-08 | 2029 | 358 | Administrative fee | 20000000 | 54054.0541 | 20% | Devex | Cash | 54054.0541 | W+BESS | 108108.1081 | 54054.0541 | 108108.1081 | 54054.0541 | Profit Ventus+Solmentore | 5579168.399 | 27895.842 | 4617182.6738 | 23085.9134
| 2028-11-09 | 2028-11-09 | 2028-11-09 | 2028 | 53 | Report fee | 12000000 | 32432.4324 | 20% | Devex | Cash | 32432.4324 | W+BESS | 64864.8649 | 32432.4324 | 64864.8649 | 32432.4324 | Profit + DSA Ventus+Solmentore | 7169446.1768 | 35847.2309 | 6207460.4516 | 31037.3023
Legal costs | Continuous | Continuous | Continuous | 2027 | 0 | Legal costs | 7400000 | 20000 | 20% | Devex | Cash | 20000 |  | 40000 | 20000 | 40000 | 20000
Financial costs | Continuous | Continuous | Continuous | 2027 | 0 | Financial costs | 29600000 | 80000 | 20% | Devex | Cash | 80000 |  | 160000 | 80000 | 160000 | 80000
RtB | 2029-03-24 | 2029-03-24 | 2029-03-24 | 2029 | 283 | Land purchase price | 91200000 | 246486.4865 | 20% | Land | Cash | 246486.4865 |  | 492972.973 | 246486.4865 | 492972.973 | 246486.4865 | Summary by category | Amount (EUR) | Interest - freeze | Interest - no freeze
Contingency | Continuous | Continuous | Continuous | 2028 | 0 | Contingency | 107908615.6245 | 291644.9071 | 20% | Devex | Cash | 291644.9071 |  | 583289.8142 | 291644.9071 | 583289.8142 | 291644.9071 | Fee | 16216.2162 | 5782.2651 | 7038.281
TOTAL WITH BONDS AND CONN FEE | [6 empty] | 23978601775.8694 | 64807031.8267 |  |  |  | 64807031.8267 |  | 74119526.0521 | 9312494.2254 | 77326145.1361 | 12519113.3095 | Bond - bank guarantee | 24018918.9189 | 3370372.6718 | 4174868.4392
TOTAL WITH BONDS AND CONN FEE /MW (FOR WIND) | [6 empty] | 119893008.8793 | 324035.1591 |  |  |  | 324035.1591 |  | 370597.6303 | 46562.4711 | 386630.7257 | 62595.5665 | Bond - cash deposit | 2432432.4324 | 802506.368 | 987207.0526
TOTAL WITHOUT BONDS AND CONN FEE | [6 empty] | 1186994771.8694 | 3208093.978 |  |  |  | 3208093.978 |  | 6405754.005 | 3197660.0269 | 6407010.0209 | 3198916.0428 | Refund - bank guarantee | -3291891.8919 | -261771.6979 | -366152.1748
TOTAL WITHOUT BONDS AND CONN FEE /MW (FOR WIND) | [6 empty] | 5934973.8593 | 16040.4699 |  |  |  | 16040.4699 |  | 32028.77 | 15988.3001 | 32035.0501 | 15994.5802 | Connection fee | 38439478.3892 | 2203726.8565 | 4524273.9496
TOTAL BONDS AND CONN FEE | [6 empty] | 22791607004 | 61598937.8486 |  |  |  | 61598937.8486 |  | 67713772.0471 | 6114834.1984 | 70919135.1153 | 9320197.2666 | Land | 425379.7297 | 425379.7297 | 425379.7297
[18 empty] | Devex | 2766498.0321 | 2766498.0321 | 2766498.0321
[18 empty] | Total | 64807031.8267 | 9312494.2254 | 12519113.3095
Disclaimers: 1. The connection fee will be defined based on the declaration of the SPV and the TSO's procedure (direct costs). 2. The met mast costs were calculated based on a previous offer without site visit. 3. The environmental, archaeological, geotechnical assessment, topography fee and other project development fees were calculated based on the respective fees of PV projects in Hungary. 4. Significant legislative changes are expected in connection with the cable right permitting, the associated costs cannot be accurately determined as of yet. Expectations are included. 5. The design fee is calculated based on a non binding offer, it will be updated with finalized technical details. 6. Items provided by bank guarantee are calculated with a 6% interest. 7. Interest is calculated with the exact dates and compounds yearly. 8. The TSO/DSO application bond cannot be provided in bank guarantee, therefore it is calculated as a cash deposit and the indirect connection fee is deducted with it. 9. With the MEKH performance bond an extra 50% is calculated. 10. Cash deposits, the application fee and the connection fee are calculated with a 12% interest. Devex and land items are calculated with a 20% interest, with a minimum return of 2x the principal. 11. Interest frozen at 2029.06.30.: interest accrues until 2029.06.30. only. No interest freeze: interest accrues until the exit on 2029.12.31.
Formulas:
Expected start date = [Expected start date, row above]+15
Expected start date = [Expected start date, row above]
Expected end date = [Expected start date]
Expected end date = [Expected start date]+30
Expected payment date = [Expected start date]
Expected payment date = [Expected end date]
Note on I18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A kiegészítő biztosítékot nem kell levonni innen?
Note on K18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ez hogyhogy nem At-risk loan?