## Slide 1
Project Bora
RtB exit and tender bid strategies
11 October 2026

## Slide 2: Bora overview
Bora overview
Tender scoring
Tender strategies
Cost per tender point
RtB price bridge
RtB returns
Summary
200 MVA onshore wind with battery storage – technical data and deal terms
Item | Assumption
Site and grid | 
Grid node | Szombathely OVIT (SZHO B 132.00)
Grid connection capacity | 200 MVA
Installed wind (Strategy 1) | 261 MW (+30.5% overbuild)
Battery storage (Strategy 1) | 90 MW × 4 h
Timeline | 
Ready to build / RtB sale | 30-Jun-29 / 31-Mar-30
NTP / COD | 30-Sep-29 / 30-Sep-31
The RtB premium is paid on the 200 MVA connection. The sale-at-COD price is per installed MW and is reduced by the clipping estimate (Strategy 1: 4.7%). The developer success fee accrues from signing to the sale.
Source: Bora IC model, 11 Oct 2026.
Transaction structure | Terms
Joint venture and developer | 
JV with A.RES (net proceeds) | FEP 70% / A.RES 30%
Developer success fee (DSA) | 2.5 k€/MW p.a. on installed MW, capped at 10 k€/MW
Signing fee to current owners | €0.25m
Devex incl. contingency | €3.14m
Exit prices | 
RtB premium | 150 k€/MW on 200 MVA = €30.0m
Sale at COD – price input | 2,450 (European) / 2,100 (Chinese) k€/MW

## Slide 3: Tender scoring – what can be offered and what it scores
Bora overview
Tender scoring
Tender strategies
Cost per tender point
RtB price bridge
RtB returns
Summary
Offerable range, band thresholds and the weighted points each band adds to the 100-point total
Criterion | Offerable | Max. | Thresholds → weighted points |  |  |  |  |  |  |  |  |  | 
ÖSZ-1 Municipal one-off (k€/MW) | 0 – 50 | 20 | > 10 | > 15 | > 20 | > 25 | > 30 | > 35 | > 40 | > 45 | ≥ 50 |  | 
points |  |  | 2 | 4 | 6 | 8 | 11 | 14 | 16 | 18 | 20 |  | 
ÖSZ-2 Community (€/MWh) | 0 – 3.0 | 15 | > 2 | > 2.1 | > 2.2 | > 2.3 | > 2.4 | > 2.5 | > 2.6 | > 2.7 | > 2.8 | > 2.9 | ≥ 3
points |  |  | 0.75 | 1.5 | 3 | 4.5 | 6 | 7.5 | 9 | 10.5 | 12 | 13.5 | 15
ÖSZ-3 Overbuild (% above MVA) | 0 – 50+ | 10 | > 2 | ≥ 5 | ≥ 10 | ≥ 15 | ≥ 20 | ≥ 25 | ≥ 30 | ≥ 35 | ≥ 40 | > 50 | 
points |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 
ÖSZ-4 Battery (% of wind, ≥ 4 h) | 0, or 5 – 50+ | 15 | ≥ 5 | ≥ 10 | ≥ 15 | ≥ 20 | ≥ 25 | ≥ 30 | ≥ 35 | ≥ 40 | > 50 |  | 
points |  |  | 3 | 4.5 | 6 | 7.5 | 9 | 10.5 | 12 | 13.5 | 15 |  | 
ÖSZ-5 Accept partial award | Yes / No | 5 | yes → 5 |  |  |  |  |  |  |  |  |  | 
ÖSZ-6 Performance security (%) | 100 – 200 | 5 | > 100 | ≥ 120 | ≥ 130 | ≥ 140 | ≥ 150 | ≥ 160 | ≥ 170 | ≥ 180 | ≥ 190 | ≥ 200 | 
points |  |  | 0.5 | 1 | 1.5 | 2 | 2.5 | 3 | 3.5 | 4 | 4.5 | 5 | 
ÖSZ-7 Brownfield site (≥ 70 %) | Yes / No | 10 | yes → 10 – not available at this node |  |  |  |  |  |  |  |  |  | 
ÖSZ-8 Shared connection | Yes / No | 5 | yes → 5 |  |  |  |  |  |  |  |  |  | 
ÖSZ-9a EU-made turbines | Yes / No | 12 | yes → 12 – European-turbine routes |  |  |  |  |  |  |  |  |  | 
ÖSZ-9b EU-made transformer | Yes / No | 3 | yes → 3 – European-turbine routes |  |  |  |  |  |  |  |  |  | 
Total |  | 100 |  |  |  |  |  |  |  |  |  |  | 
A commitment below the first band scores 0 and keeps the bid valid; the only validity rule is installed wind at least equal to the connection MVA. Battery points need at least 4 hours and no more battery MW than wind MW. Performance security is a percentage of the tender minimum. EU-equipment points count on the European-turbine routes only.
Source: Bora IC model, 11 Oct 2026.

## Slide 4: Tender strategies
Bora overview
Tender scoring
Tender strategies
Cost per tender point
RtB price bridge
RtB returns
Summary
Commitment and points per criterion for the five bids, with the offerable range and maximum points
 |  |  | Strategy 0 – Zero bid |  | Strategy 1 – Current bid |  | Strategy 2 – Free points |  | Strategy 3 – Cost-efficient ~70 pts |  | Strategy 4 – Maximum score | 
Criterion | Range | Max | Offer | Pts | Offer | Pts | Offer | Pts | Offer | Pts | Offer | Pts
ÖSZ-1 Municipal (k€/MW) | 0 – 50 | 20 | 0 | 0.0 | 20 | 4.0 | 20 | 4.0 | 50 | 20.0 | 50 | 20.0
ÖSZ-2 Community (€/MWh) | 0 – 3.0 | 15 | 0.0 | 0.0 | 2.0 | 0.0 | 2.0 | 0.0 | 2.0 | 0.0 | 3.0 | 15.0
ÖSZ-3 Overbuild (%) | 0 – 50+ | 10 | 0.0% | 0.0 | 30.5% | 7.0 | 40.0% | 9.0 | 40.0% | 9.0 | 54.0% | 10.0
ÖSZ-4 Battery (4 h) | 0, or 5 – 50+ | 15 | 0 MW | 0.0 | 90 MW | 10.5 | 90 MW | 10.5 | 90 MW | 10.5 | 157 MW | 15.0
ÖSZ-5 Partial award | Yes / No | 5 | No | 0.0 | No | 0.0 | Yes | 5.0 | Yes | 5.0 | Yes | 5.0
ÖSZ-6 Security (% of min.) | 100 – 200 | 5 | 100% | 0.0 | 150% | 2.5 | 160% | 3.0 | 200% | 5.0 | 210% | 5.0
ÖSZ-8 Shared connection | Yes / No | 5 | No | 0.0 | No | 0.0 | Yes | 5.0 | Yes | 5.0 | Yes | 5.0
ÖSZ-9 EU equipment | Yes / No | 12 + 3 | No | 0.0 | Turbine | 12.0 | Turbine + transf. | 15.0 | Turbine + transf. | 15.0 | Turbine + transf. | 15.0
Score – EU-turbine routes |  |  |  | 0.0 |  | 36.0 |  | 51.5 |  | 69.5 |  | 90.0
Score – CN-turbine routes |  |  |  | 0.0 |  | 24.0 |  | 36.5 |  | 54.5 |  | 75.0
Installed wind / clipping |  |  | 200 MW / 0.0% |  | 261 MW / 4.7% |  | 280 MW / 8.0% |  | 280 MW / 8.0% |  | 308 MW / 14.6% | 
Judgement calls: the 40% overbuild in Strategies 2–3 adds points without an RtB price effect (the premium is on the connection MVA) but raises the clipping loss to 8.0%; performance security of 160% costs €0.14m of RtB price. Brownfield is not available at this node. All five bids are valid – the zero bid included – and carry the node-cap eligibility flag.
Source: Bora IC model, 11 Oct 2026.

## Slide 5: Cost per tender point at the RtB exit
Bora overview
Tender scoring
Tender strategies
Cost per tender point
RtB price bridge
RtB returns
Summary
RtB price given up per point added to the current bid (European-turbine score)
Criterion | Step | Points | RtB price (€m) | RtB k€ per point | FEP k€ per point
Points without an RtB price effect |  |  |  |  | 
ÖSZ-5 Partial award | Yes | 5.0 | – | – | –
ÖSZ-8 Shared connection | Yes | 5.0 | – | – | –
ÖSZ-9b EU transformer | Yes | 3.0 | – | – | –
ÖSZ-3 Overbuild | 30.5% → 40% | 2.0 | – | – | 109–121
Points that reduce the RtB price |  |  |  |  | 
ÖSZ-6 Performance security | 150% → 200% | 2.5 | 0.7 | 261 | 537
ÖSZ-1 Municipal one-off (k€/MW) | 20 → 50 | 16.0 | 5.0 | 278–417 | 195–292
ÖSZ-2 Community (€/MWh) | 2.0 → 3.0 | 15.0 | 5.3 | 178–711 | 124–498
ÖSZ-4 Battery (% of wind) | 34.5% → 51% | 4.5 | 8.0 | 167–3,557 | 128–2,720
Each step adds one band step of one criterion to Strategy 1. RtB price = the promise's present value to the buyer, passed through in full. FEP k€ per point is FEP's after-tax profit change per point (after the A.RES share; higher where FEP also pays fees on extra installed MW). Ranges leave out one band edge: municipal 45 → 45.01 k€/MW adds 2 points for 2 k€.
Source: Bora IC model, 11 Oct 2026.
Not priced in the RtB price
EU turbine: 12 points on the European routes bind the buyer to European turbines – €117.5m more capex at 261 MW (€126.0m at 280 MW) if it would otherwise build Chinese
EU transformer: 3 points; a Chinese-equipment buyer gives up a substation saving of €1.2m
Overbuild clipping: the loss rises from 4.7% to 8.0% (14.6% in Strategy 4) and lowers the buyer's yield; the RtB price is on the connection MVA
Partial award and shared connection: scored at no modelled cost

## Slide 6: RtB price bridge – vs the current bid
Bora overview
Tender scoring
Tender strategies
Cost per tender point
RtB price bridge
RtB returns
Summary
Gross premium of €30.0m plus or minus the present value of each strategy's promises vs the current bid
RtB price | Unit | Strategy 0 – Zero bid | Strategy 1 – Current bid | Strategy 2 – Free points | Strategy 3 – Cost-efficient ~70 pts | Strategy 4 – Maximum score
Gross RtB premium | €m | 30.0 | 30.0 | 30.0 | 30.0 | 30.0
Municipal contribution vs current bid | €m | +3.3 | 0.0 | 0.0 | (5.0) | (5.0)
Community contribution vs current bid | €m | +8.6 | 0.0 | 0.0 | 0.0 | (5.6)
Battery storage vs current bid | €m | +15.9 | 0.0 | 0.0 | 0.0 | (11.9)
Performance security vs current bid | €m | +1.1 | 0.0 | (0.1) | (0.7) | (1.7)
Price effect vs current bid | €m | +28.9 | 0.0 | (0.1) | (5.7) | (24.2)
Effective RtB price | €m | 58.9 | 30.0 | 29.9 | 24.3 | 5.8
Effective price per MVA | k€ | 294.7 | 150.0 | 149.3 | 121.6 | 28.9
Score – European / Chinese turbine | pts | 0.0 / 0.0 | 36.0 / 24.0 | 51.5 / 36.5 | 69.5 / 54.5 | 90.0 / 75.0
Present value to the buyer at the RtB sale (after tax) of each promise relative to the current bid, passed through in full. The zero bid promises less than the current bid, so its price rises by the saving. Segments under €1m are labelled in the table only.
Source: Bora IC model, 11 Oct 2026.
Chart: Effective RtB price and where the €30.0m premium goes (€m)
| Strategy 0 – Zero bid | Strategy 1 – Current bid | Strategy 2 – Free points | Strategy 3 – Cost-efficient ~70 pts | Strategy 4 – Maximum score
Effective price (up to the gross premium) | 30 | 30 | 29.8639 | 24.3128 | 5.788
Municipal | 5.0064 | 5.0064
Community | 5.6356
Battery storage | 11.8767
Performance security | 0.13615 | 0.68073 | 1.6932
Saving vs current bid | 28.9302

## Slide 7: RtB returns per strategy
Bora overview
Tender scoring
Tender strategies
Cost per tender point
RtB price bridge
RtB returns
Summary
FEP returns at the RtB sale (31-Mar-30) with the A.RES share and the developer success fee
Metric | Unit | Strategy 0 – Zero bid | Strategy 1 – Current bid | Strategy 2 – Free points | Strategy 3 – Cost-efficient ~70 pts | Strategy 4 – Maximum score
Effective RtB price | €m | 58.9 | 30.0 | 29.9 | 24.3 | 5.8
Distributable proceeds | €m | 48.3 | 16.6 | 15.9 | 9.5 | (11.1)
to FEP (70%) | €m | 33.8 | 11.6 | 11.1 | 6.6 | (8.5)
to A.RES (30%) | €m | 14.5 | 5.0 | 4.8 | 2.8 | (2.6)
Developer success fee (DSA) | €m | 1.7 | 2.2 | 2.4 | 2.4 | 2.6
FEP net profit (after tax) | €m | 37.6 | 15.2 | 14.7 | 10.0 | (5.3)
FEP IRR | % | 50.2% | 20.9% | 20.0% | 13.7% | −7.5%
FEP MOIC | x | 1.82x | 1.31x | 1.30x | 1.20x | 0.90x
FEP NPV at 8% | €m | 24.5 | 7.3 | 6.8 | 3.2 | (8.6)
FEP peak exposure | €m | 46.0 | 48.5 | 48.9 | 49.9 | 52.0
RtB premium sensitivity |  |  |  |  |  | 
FEP IRR at 150 k€/MW | % | 50.2% | 20.9% | 20.0% | 13.7% | −7.5%
FEP IRR at 200 k€/MW | % | 57.9% | 29.6% | 28.7% | 22.5% | 3.2%
FEP IRR at 250 k€/MW | % | 65.2% | 37.8% | 36.9% | 30.8% | 12.2%
Premium for Strategy 1's IRR | k€/MW | beats it even at zero premium | 150.0 | 154.8 | 190.6 | 301.4
Distributable proceeds are split 70% FEP / 30% A.RES; A.RES' share is floored at minus the success fee (2.5 k€/MW a year on the installed MW, capped at 10 k€/MW). Strategy 0 would match Strategy 1's IRR at a premium of −17.6 k€/MW, i.e. it beats Strategy 1 even at zero premium.
Source: Bora IC model, 11 Oct 2026.
Chart: FEP IRR by RtB premium
| Strategy 0 | Strategy 1 | Strategy 2 | Strategy 3 | Strategy 4
Premium 150 k€/MW | 0.50156 | 0.20894 | 0.20042 | 0.13689 | -0.074915
Premium 200 k€/MW | 0.57884 | 0.29606 | 0.2871 | 0.2251 | 0.031706
Premium 250 k€/MW | 0.65234 | 0.37823 | 0.36885 | 0.30816 | 0.12195

## Slide 8: Summary – RtB exit against building
Bora overview
Tender scoring
Tender strategies
Cost per tender point
RtB price bridge
RtB returns
Summary
FEP IRR / MOIC per strategy: RtB sale against sale at COD and hold to maturity
Route | Unit | Strategy 0 – Zero bid | Strategy 1 – Current bid | Strategy 2 – Free points | Strategy 3 – Cost-efficient ~70 pts | Strategy 4 – Maximum score
Tender score – European / Chinese | pts | 0.0 / 0.0 | 36.0 / 24.0 | 51.5 / 36.5 | 69.5 / 54.5 | 90.0 / 75.0
RtB sale | IRR / MOIC | 50.2% / 1.82x | 20.9% / 1.31x | 20.0% / 1.30x | 13.7% / 1.20x | −7.5% / 0.90x
Sale at COD – European turbine | IRR / MOIC | 38.2% / 1.74x | 31.4% / 1.54x | 29.0% / 1.48x | 27.4% / 1.45x | 16.3% / 1.25x
Sale at COD – Chinese turbine | IRR / MOIC | 47.4% / 2.02x | 42.1% / 1.80x | 40.8% / 1.75x | 39.0% / 1.70x | 29.6% / 1.50x
Hold to maturity – European | IRR / MOIC | 9.7% / 5.65x | 10.0% / 6.13x | 9.7% / 5.95x | 9.7% / 5.99x | 9.0% / 5.64x
Hold to maturity – Chinese | IRR / MOIC | 12.4% / 6.95x | 13.1% / 7.79x | 12.9% / 7.62x | 12.9% / 7.68x | 12.3% / 7.40x
COD price after clipping and promise effect (EU / CN) | k€/MW | 2,498 / 2,148 | 2,336 / 2,002 | 2,254 / 1,932 | 2,254 / 1,932 | 2,072 / 1,773
The sale-at-COD price is 2,450 / 2,100 k€ per installed MW, adjusted for clipping and for the post-COD promises relative to the current bid; on the build routes the turbine follows the route. All results pass the model's integrity checks in every strategy and route.
Source: Bora IC model, 11 Oct 2026.
Key messages
Zero bid: 0 points and still valid; its promises are worth +€28.9m vs the current bid, so the effective price is €58.9m and FEP earns 50.2% / 1.82x
Free points: Strategy 2 scores 51.5 instead of 36.0 for €0.1m of RtB price; IRR 20.0% vs 20.9%
About 70 points: Strategy 3 gives up €5.7m; IRR 13.7%; needs 190.6 k€/MW to match Strategy 1
Maximum score: effective price €5.8m, FEP loss €5.3m (IRR −7.5%); needs 301.4 k€/MW
Node-cap flag: 200 MVA at one node against the 100 MVA cap, on every strategy – an eligibility flag, not an integrity failure
Information only: bare project at 150 k€/MW
vs the zero bid | Strategy 0 | Strategy 1 | Strategy 2 | Strategy 3 | Strategy 4
Price effect (€m) | 0.0 | (28.9) | (29.1) | (34.6) | (53.1)
Effective price (€m) | 30.0 | 1.1 | 0.9 | (4.6) | (23.1)
FEP IRR | 25.3% | −10.0% | −10.8% | −21.0% | −56.9%
FEP MOIC | 1.38x | 0.87x | 0.86x | 0.73x | 0.34x
Caveat: the model has no battery revenue, so the battery is a pure cost to the buyer – €15.9m of Strategy 1's €28.9m. The model itself prices promises against the current bid.