## Slide 1
Project Bora
BORA 1 and BORA 2 capacity bids
Approval of the tender commitments, 2 × 100 MVA, Szombathely OVIT
12‑Oct‑2026

## Slide 2: Submit both bids at 85 / 68.25 points: FEP earns €6.5m / €6.7m at the RtB exit, a 22.2% / 22.9% IRR
Executive summary
Commitments
Economics – RtB exit
Economics – COD and HTM
Risks and mitigants
Against the zero bid, the commitments cost €0.8m / €0.7m of RtB profit and 2.4 / 1.9 pp of HTM IRR, and add €23.4m / €19.5m to the all-in commitment.
Item | Unit | Zero bid | BORA 1 | BORA 2
Points (EU turbine) | points | 0 | 85 | 68.25
FEP profit – RtB route | € m | 7.4 | 6.5 | 6.7
FEP IRR – RtB route | % | 25.8% | 22.2% | 22.9%
FEP IRR – sale at COD | % | 49.6% | 37.8% | 40.5%
FEP IRR – hold to maturity | % | 11.9% | 9.5% | 9.9%
All-in commitment if built (securities, development, construction, financing) | € m | 147.8 | 171.2 | 167.3
Approval requested and timetable
Submit both bids by 30‑Oct‑2026: municipal 50 k€/MW; community 3.00 / 2.01 €/MWh; overbuild 51% / 40% (not built); BESS 51% / 40% of MVA, 4 h; PB at the 1.0x minimum; partial award, shared connection, EU turbines and transformers.
Day one, at submission: participation fee €0.008m per bid (cash) and bid guarantee €1.4m / €1.2m.
After award (13‑Dec‑2026): PB guarantee €7.0m / €6.1m by 28‑Dec‑2026, which replaces the bid guarantee; TSO cash security €1.2m per bid by 30‑Dec‑2026.
Before submission: legal confirmation that the two bids sit within the 100 MVA group cap per node.
Post-tax, FEP share, EU turbine, base case (overbuild not built, BESS built, pro-rata PB call); RtB exit 31‑Dec‑2029. Zero bid = every commitment at its zero level.
Source: Bora_Bid_Model.xlsm, 12 Oct 2026.

## Slide 3: Municipal buys 20 points for 0.4 pp of HTM IRR; BESS (1.2 pp) and community (0.6 pp) carry the return cost on BORA 1
Executive summary
Commitments
Economics – RtB exit
Economics – COD and HTM
Risks and mitigants
Each commitment is measured alone against the zero bid; the PB stays at the 1.0x minimum because 2.0x adds 5 points for one more PB of guarantee.
Commitment (B1 / B2) | Offered | Points | Δ RtB profit € m | Δ COD IRR pp | Δ HTM IRR pp | Δ deposits and guarantees € m | Logic
Municipal one-off (ÖSZ-1) | 50 / 50 k€/MW | 20 / 20 | 0.0 / 0.0 | −1.2 / −1.2 | −0.4 / −0.4 | 0.0 / 0.0 | Paid at COD, after the RtB exit: no FEP cash on the RtB route.
Community contribution (ÖSZ-2) | 3.00 / 2.01 €/MWh | 15 / 0.75 | 0.0 / 0.0 | −2.6 / −1.7 | −0.6 / −0.4 | 0.0 / 0.0 | Operating cost after COD. At the band floor, BORA 2 earns 0.75 points.
Overbuild (ÖSZ-3) | 51% / 40% | 10 / 9 | (0.5) / (0.4) | −1.1 / −0.9 | −0.2 / −0.2 | +1.4 / +1.1 | Not built: the cost is the larger PB and its pro-rata call.
BESS power (ÖSZ-4), 4 h | 51% / 40% of MVA | 15 / 13.50 | (0.4) / (0.3) | −6.5 / −5.1 | −1.2 / −1.0 | +2.8 / +2.2 | Sized with the overbuild and built; valued at cost, with no BESS revenue.
PB multiple (ÖSZ-6) | 1.0x / 1.0x | 0 / 0 | 0.0 | 0.0 | 0.0 | 0.0 | Not raised: 2.0x adds 5 points for one more PB of €7.0m / €6.1m of guarantee.
Partial award (ÖSZ-5), shared connection (ÖSZ-8), EU turbines / transformers (ÖSZ-9) | yes | 5 / 5 / 12 / 3 each bid | 0.0 | 0.0 | 0.0 | 0.0 | No cash or return impact. EU sourcing is in the base cost (turbine 600 k€/MW).
Full bid vs zero bid |  | 85 / 68.25 | (0.8) / (0.7) | −11.7 / −9.1 | −2.4 / −1.9 | – | The rows do not add to the total because the commitments interact.
Δ = zero bid plus that commitment alone, minus the zero bid. Zero levels: municipal 0, community 0, overbuild 0%, BESS 0%, PB 1.0x, yes/no items no. Δ deposits and guarantees = extra security posted, not a call. ÖSZ-6: 5 points at 2.0x (Kiírás X.4 bf, Annex 4). Brownfield (ÖSZ-7) is not offered.
Source: Bora_Bid_Model.xlsm, 12 Oct 2026.

## Slide 4: At the RtB exit FEP recovers its cash and earns €6.5m / €6.7m, a 1.25x / 1.26x MOIC
Executive summary
Commitments
Economics – RtB exit
Economics – COD and HTM
Risks and mitigants
FEP funds €24.9m per bid to 31‑Dec‑2029 and carries the PB guarantee. Of the €14.5m RtB price net of sale costs, FEP takes €11.1m / €11.1m.
Item | Unit | BORA 1 | BORA 2
RtB price | € m | 15.0 | 15.0
Receipts at the exit | € m | 32.9 | 32.9
Outlays: devex, land, deposits, connection fees, signing | € m | (24.9) | (24.9)
Guarantee fees (6% carry) | € m | (1.3) | (1.1)
Tax at the exit | € m | (0.1) | (0.1)
FEP profit – RtB route | € m | 6.5 | 6.7
FEP profit – RtB route, low-premium case (100 k€/MVA) | € m | 3.0 | 3.2
Exit split – FEP: claims + 70% | € m (k€/MW) | 11.1 (73) | 11.1 (79)
Exit split – A.RES: DSA + 30% | € m (k€/MW) | 3.4 (23) | 3.4 (25)
Exit split – total | € m (k€/MW) | 14.5 (96) | 14.5 (104)
Securities to the exit
Bid guarantee €1.4m / €1.2m, 30‑Oct‑2026 to 28‑Dec‑2026.
PB guarantee €7.0m / €6.1m from 28‑Dec‑2026; the buyer replaces it at the exit.
Cash: TSO security €1.2m (30‑Dec‑2026) and connection fees €1.4m + €18.8m (08‑Jan‑2029). The buyer reimburses €21.4m at the exit.
RtB price 150 k€/MVA × 100 MVA, per the Bora scenarios meeting file (Bora!N5), confirmed 12‑Oct‑2026. Receipts = recoverable principal, land and claims, plus 70% of the distributable. Per-MW figures use installed wind of 151 / 140 MW. The participation fee is not recovered.
Source: Bora_Bid_Model.xlsm, 12 Oct 2026.

## Slide 5: All-in cost of 1,642 / 1,612 k€ per built MW against a 2,450 k€/MW COD price; HTM NPV €13.4m / €17.2m at 8.0%
Executive summary
Commitments
Economics – RtB exit
Economics – COD and HTM
Risks and mitigants
The commitments reduce HTM NPV by €18.1m / €14.2m against the zero bid; construction is €150.9m / €148.3m of the all-in commitment.
Item | Unit | Zero bid | BORA 1 | BORA 2 | Δ B1 | Δ B2
FEP NPV – sale at COD | € m | 44.6 | 30.8 | 33.6 | (13.9) | (11.0)
FEP NPV – hold to maturity | € m | 31.4 | 13.4 | 17.2 | (18.1) | (14.2)
All-in cost to COD per built MW | k€/MW | – | 1,642 | 1,612 | – | –
COD sale price per built MW | k€/MW | – | 2,450 | 2,450 | – | –
Securities: cash posted and guarantees | € m | – | 8.2 | 7.3 | – | –
Devex, land, signing and DD | € m | – | 3.5 | 3.5 | – | –
Construction capex incl. connection fees, municipal and pre-COD lease | € m | – | 150.9 | 148.3 | – | –
Financing: IDC, debt fees, guarantee fees | € m | – | 8.5 | 8.2 | – | –
Memo, not in the commitment: PB call, overbuild not built | € m | – | 1.4 | 1.1 | – | –
Sale at COD: FEP proceeds of €124.4m / €127.2m on a €245.0m price, a 1.78x / 1.85x MOIC.
Hold to maturity: 4.89x / 5.13x MOIC; minimum DSCR 1.33x / 1.37x.
NPV at 8.0%. COD 30‑Sep‑2031, 100 MW built; PPA 90 €/MWh; gearing 60.0%. HTM includes the buy-out of the developer at the RtB exit date. The four breakdown lines sum to the all-in commitment on slide 2.
Source: Bora_Bid_Model.xlsm, 12 Oct 2026.

## Slide 6: Main risk: the unbuilt overbuild – a PB call, a 3-year group exclusion and 33.8 / 28.6 MVA of connection right lost
Executive summary
Commitments
Economics – RtB exit
Economics – COD and HTM
Risks and mitigants
The base COD and HTM returns include the pro-rata call; the lost MVA and any deduction from the RtB price are not in the returns.
Risk | Exposure (B1 / B2) | Mitigant
PB call on the unbuilt overbuild: pro rata (Kiírás XII.12) or full (XIII.17, GYIK Q72) | Pro rata €1.4m / €1.1m (base). Full call €7.0m / €6.1m: COD IRR 35.8% / 38.7%, HTM IRR 9.1% / 9.5% | PB at the 1.0x minimum. Part of the call may be deducted from the RtB price.
3-year group exclusion (Kiírás VII.2 n, GYIK Q71) | Any PB call triggers it, the base pro-rata call included, for both bids. The call falls after COD, so it is likely to hit the group then holding the SPV. | Allocate it in the RtB SPA.
Connection right lost pro rata (Kiírás XII.12, GYIK Q28) | 33.8 / 28.6 MVA; not reflected in generation or price. | The buyer can build the overbuild (card).
100 MVA group cap per node (Kiírás V.7, GYIK Q52) | Both bids are invalid if FEP, A.RES and the SPVs count as one company group. | Legal confirmation before submission.
ÖSZ-4 scored on installed wind (GYIK Q20) | Points fall to 80.50 / 63.75; returns unchanged. | Ranking risk only; the commitment is the same.
BESS valued at cost only | −6.5 / −5.1 pp of COD IRR, with no BESS revenue or sale value. | Conservative: any BESS revenue is upside.
Why the base does not build the overbuild
The grid connection stays at 100 MVA. Building the overbuild lifts the all-in cost to COD from €164.2m / €161.2m to €217.9m / €203.3m. In that case COD IRR is 54.4% / 53.8% and HTM IRR is 11.5% / 11.6%. The build decision passes to the buyer at RtB.
PB call tested 6 months after COD. Pro rata = shortfall share × the wind PB (GYIK Q28/Q30). Full-call and overbuild-built figures are alternative cases.
Source: Bora_Bid_Model.xlsm, 12 Oct 2026.